## Backlog
ID | MiniApp | Track | Priority | Phase | Title | Description | Notes/Dependencies
DISC-01 | Discover & Feed | Engineering | P0 | Harden Core | Fix ranked-feed pagination past offset 400 | Ranked feed pagination degrades at scale beyond offset 400; build a precomputed rank+decay cron job so deep pagination stays performant. | Blocks scaling Discover once vertical content volume grows
DISC-02 | Discover & Feed | Engineering | P0 | Harden Core | Add consistent infinite scroll to Profile/Circle-posts/Bookmarks/Search | Profile, Circle-posts, Bookmarks, and Search currently hardcode no-more-pages while Feed/Discover/Tag get real cursor pagination; bring all list views to the same pattern.
DISC-03 | Discover & Feed | Design | P0 | Harden Core | Design mobile fallback for PostSidebar | PostSidebar is desktop-only and disappears entirely on mobile with no fallback; design a mobile-appropriate equivalent (e.g. bottom sheet or inline module).
DISC-04 | Discover & Feed | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Add category/subcategory schema fields to Post model | Extend the Post schema to carry a primary vertical (Fashion/Technology/Lifestyle) plus subcategory, enabling the new Discover taxonomy. | Blocks DISC-06 and vertical landing routes
DISC-05 | Discover & Feed | Design | P1 | Fashion/Tech/Lifestyle Taxonomy | Design Discover nav for Fashion/Technology/Lifestyle sections | Design top-level Discover navigation with Fashion/Technology/Lifestyle sections and subcategory filter chips reusing the existing filter/ component patterns.
DISC-06 | Discover & Feed | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Extend filter system and feed params for category/subcategory | Add category/subcategory filter support to the getFeedDiscoverParams API and the shared filter/ UI system. | Depends on DISC-04
DISC-07 | Discover & Feed | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Backfill taxonomy tags on existing content via AI agent | Use the existing AI agent's category-suggestion capability to backfill vertical/subcategory tags on already-ingested RSS and native posts. | Depends on DISC-04
DISC-08 | Discover & Feed | Marketing | P0 | Harden Core | Audit content-mix gaps against launch taxonomy | Review current post/source inventory against the new Fashion/Technology/Lifestyle taxonomy to identify subcategories with little or no content before launch.
DISC-09 | Discover & Feed | Marketing | P1 | Fashion/Tech/Lifestyle Taxonomy | Plan RSS source acquisition for Lifestyle vertical | Identify and shortlist RSS sources to onboard for the new Lifestyle vertical, since no lifestyle content currently exists in the platform.
DISC-10 | Discover & Feed | Design | P2 | Mini-Apps Wave 1 | Redesign Discover landing page with per-vertical hero rails | Add dedicated hero rails for Fashion, Technology, and Lifestyle on the Discover landing page once each vertical has sufficient content density. | Depends on FASH/TECH/LIFE launch rows
COMM-01 | Community & Circles | Engineering | P1 | Harden Core | Add circle moderator role management | Allow circle owners to assign and revoke a moderator role for other members, currently unsupported.
COMM-02 | Community & Circles | Engineering | P1 | Harden Core | Add circle-level content moderation hooks | Wire circle-scoped moderation actions into the existing rule-based policy engine so circles can enforce their own posting rules. | Depends on existing moderation policy engine
COMM-03 | Community & Circles | Engineering | P1 | Harden Core | Add circle edit/delete for owners | Circle owners currently cannot edit circle details or delete a circle; add both operations with appropriate safeguards.
COMM-04 | Community & Circles | Design | P1 | Harden Core | Design circle moderator management UI | Design the permissions and moderator-assignment surface for circle owners. | Depends on COMM-01
COMM-05 | Community & Circles | Engineering | P2 | Mini-Apps Wave 1 | Add basic circle analytics for owners | Give circle owners visibility into member growth and post velocity over time.
COMM-06 | Community & Circles | Design | P2 | Mini-Apps Wave 1 | Adopt shared filter component in Circles directory | Replace the Circles directory's bespoke search/filter UI with the generic components/filter/ system already used in Discover and Moderation.
COMM-07 | Community & Circles | Marketing | P1 | Harden Core | Seed flagship circles per launch vertical | Recruit early members and content to launch 5-10 flagship circles across Fashion, Technology, and Lifestyle before wider promotion.
COMM-08 | Community & Circles | Marketing | P2 | Mini-Apps Wave 1 | Create circle-owner onboarding and recognition program | Build a lightweight playbook and recognition program to help circle owners grow and retain active communities.
MOD-01 | Moderation & Trust | Engineering | P0 | Harden Core | Add audit trail for auto-approve/auto-reject decisions | Log which policy rule and AI signal triggered each automated moderation decision so reviewers can understand and contest outcomes.
MOD-02 | Moderation & Trust | Engineering | P1 | Harden Core | Wire up unused agent score-post endpoint | The AI agent's /v1/score-post endpoint is built but not integrated into the moderation pipeline; connect it to the queue/policy flow.
MOD-03 | Moderation & Trust | Engineering | P1 | Harden Core | Add replay protection to AI-agent callback auth | Current internal callback auth relies on a single static secret with no replay protection; add signed, time-bound request verification.
MOD-04 | Moderation & Trust | Engineering | P1 | Mini-Apps Wave 1 | Add comment moderation and reporting | Extend the moderation queue and policy engine to cover comments, which currently have no moderation or reporting path at all.
MOD-05 | Moderation & Trust | Design | P1 | Harden Core | Design audit-trail view in moderation queue drawer | Add a decision-reasoning panel to the existing moderation queue drawer showing why a post was auto-approved or auto-rejected. | Depends on MOD-01
MOD-06 | Moderation & Trust | Marketing | P2 | Mini-Apps Wave 1 | Publish a trust/transparency piece on the moderation engine | Write and publish content positioning Centoire's rule-based policy engine and AI moderation agent as a trust differentiator versus other community platforms.
NOTIF-01 | Notifications | Engineering | P0 | Harden Core | Build Notification model service and routes | Notifications do not exist anywhere in the codebase today; build the core model, service layer, and REST routes from scratch. | Blocks all other NOTIF rows
NOTIF-02 | Notifications | Engineering | P0 | Harden Core | Emit notifications for follow/comment/upvote/mention/moderation events | Hook notification creation into existing follow, comment, vote, mention, and moderation-decision flows. | Depends on NOTIF-01
NOTIF-03 | Notifications | Engineering | P0 | Harden Core | Build notification center API with read state and pagination | Provide a paginated, mark-as-read-capable API for the notification center UI to consume. | Depends on NOTIF-01
NOTIF-04 | Notifications | Design | P0 | Harden Core | Design notification center UI | Design the bell icon, dropdown/panel, item states, and empty states for the notification center. | Depends on NOTIF-03
NOTIF-05 | Notifications | Design | P1 | Harden Core | Design notification preference settings screen | Design a granular opt-in/opt-out settings screen covering each notification category.
NOTIF-06 | Notifications | Engineering | P1 | Harden Core | Add notification preference model and enforcement | Store per-user notification preferences and check them before emitting any notification. | Depends on NOTIF-01, NOTIF-05
NOTIF-07 | Notifications | Engineering | P2 | Mini-Apps Wave 1 | Add email digest notifications | Add daily/weekly email digest notifications using the existing Resend email integration. | Depends on NOTIF-01
NOTIF-08 | Notifications | Marketing | P1 | Harden Core | Define respectful notification-defaults policy copy | Write onboarding copy and default settings that communicate a respectful, non-spammy notification philosophy from first use. | Depends on NOTIF-05
REP-01 | Reputation & Leaderboard | Engineering | P1 | Harden Core | Build leaderboard endpoint from reputation ledger | No leaderboard endpoint exists today despite the reputation ledger already recording all events; build an aggregation endpoint to surface rankings.
REP-02 | Reputation & Leaderboard | Engineering | P1 | Harden Core | Add time-windowed leaderboard views | Support weekly, monthly, and all-time leaderboard windows on top of the new endpoint. | Depends on REP-01
REP-03 | Reputation & Leaderboard | Design | P1 | Harden Core | Design leaderboard page and profile reputation badge | Design a dedicated leaderboard page plus a reputation badge/tier indicator on user profiles. | Depends on REP-01
REP-04 | Reputation & Leaderboard | Engineering | P2 | Mini-Apps Wave 1 | Add reputation-tier gating hooks | Allow reputation thresholds to unlock privileges, e.g. creator permissions, as a foundation for future gamification. | Depends on REP-01
REP-05 | Reputation & Leaderboard | Design | P2 | Mini-Apps Wave 1 | Design reputation-tier visual system | Design badges and progress indicators representing reputation tiers across profile and post surfaces. | Depends on REP-04
REP-06 | Reputation & Leaderboard | Marketing | P1 | Harden Core | Launch Top Contributors recognition campaign | Plan and launch a recognition campaign around top contributors tied to the leaderboard release to drive retention. | Depends on REP-01
SEARCH-01 | Search | Engineering | P1 | Harden Core | Add pagination to search results | Search results are currently unpaginated; add cursor-based pagination consistent with the rest of the platform.
SEARCH-02 | Search | Engineering | P2 | Mini-Apps Wave 1 | Add fuzzy/typo-tolerant search matching | Replace or augment the current Mongo $text/regex search with fuzzy matching to tolerate typos.
SEARCH-03 | Search | Engineering | P2 | Mini-Apps Wave 1 | Add search analytics logging | Log queries and zero-result rates to inform future search and content-gap decisions.
SEARCH-04 | Search | Design | P1 | Harden Core | Add infinite scroll to search results UI | Bring the search results UI to the same infinite-scroll pattern used by Feed/Discover/Tag pages. | Depends on SEARCH-01
SEARCH-05 | Search | Design | P2 | Mini-Apps Wave 2 | Design unified cross-mini-app search experience | Design a search experience that spans posts, verticals, Tools Directory, Expert Voices, and Industry Directory results. | Depends on TOOLS/EXPERT/DIR mini-apps existing
PLAT-01 | Discover & Feed | Engineering | P1 | Harden Core | Implement refresh-token rotation | Add refresh-token rotation to the JWT cookie session model to reduce long-lived-token risk.
PLAT-02 | Discover & Feed | Engineering | P1 | Harden Core | Add rate limiting to follow/unfollow endpoint | The follow/unfollow endpoint currently has no rate limiting; add abuse protection.
PLAT-03 | Discover & Feed | Engineering | P1 | Harden Core | Add account deletion flow | Build an account deletion flow including data export/removal, currently entirely missing.
PLAT-04 | Discover & Feed | Engineering | P2 | Harden Core | Fix or remove orphaned HealthPage route | HealthPage is built but unreachable from any navigation; either wire it into admin nav or remove the dead route.
PLAT-05 | Discover & Feed | Design | P1 | Harden Core | Add in-app password change to Settings | Settings currently has no in-app password-change flow; design and ship one.
PLAT-06 | Discover & Feed | Engineering | P2 | Harden Core | Replace admin role-promotion dialog bypassing API client | One admin dialog bypasses the generated API client for role promotion; refactor it to use the standard generated client.
FASH-01 | Fashion Vertical | Engineering | P0 | Fashion/Tech/Lifestyle Taxonomy | Implement Fashion vertical landing route | Build the Fashion vertical landing route with subcategory tabs (News/Runway/Design/Retail/Sustainability/Culture). | Depends on DISC-04
FASH-02 | Fashion Vertical | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Tag RSS sources by Fashion subcategory | Extend the admin-managed RSS source configuration to tag each source with a Fashion subcategory. | Depends on DISC-04
FASH-03 | Fashion Vertical | Design | P0 | Fashion/Tech/Lifestyle Taxonomy | Design Fashion vertical homepage layout | Design the Fashion vertical homepage with rails for news, runway, design, and retail content.
FASH-04 | Fashion Vertical | Design | P1 | Fashion/Tech/Lifestyle Taxonomy | Design Fashion subcategory chip and filter treatment | Design the subcategory chip/filter treatment for the Fashion vertical, reused from the shared filter/ system.
FASH-05 | Fashion Vertical | Marketing | P0 | Fashion/Tech/Lifestyle Taxonomy | Recruit initial Fashion creators and circles | Recruit an initial cohort of Fashion creators and seed Fashion-focused circles ahead of vertical launch.
FASH-06 | Fashion Vertical | Marketing | P1 | Mini-Apps Wave 1 | Run Fashion vertical launch content campaign | Plan and execute a social and email campaign around the Fashion vertical launch. | Depends on FASH-01
TECH-01 | Technology Vertical | Engineering | P0 | Fashion/Tech/Lifestyle Taxonomy | Implement Technology vertical landing route | Build the Technology vertical landing route with subcategory tabs (AI/Design Tech/Retail Tech/Supply Chain Tech/Emerging Tech). | Depends on DISC-04
TECH-02 | Technology Vertical | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Add cross-tagging for Technology content | Support cross-tagging so Technology-pillar content can co-tag Fashion or Lifestyle posts rather than existing only in isolation. | Depends on DISC-04
TECH-03 | Technology Vertical | Design | P0 | Fashion/Tech/Lifestyle Taxonomy | Design Technology vertical homepage | Design the Technology vertical homepage with rails for AI, Design Tech, Retail Tech, and Emerging Tech content.
TECH-04 | Technology Vertical | Design | P1 | Mini-Apps Wave 1 | Design visual distinction for Tech-pillar cross-tags | Design a visual treatment that distinguishes horizontal Tech-pillar tags from primary vertical tags across the UI. | Depends on TECH-02
TECH-05 | Technology Vertical | Marketing | P0 | Fashion/Tech/Lifestyle Taxonomy | Source fashion-tech RSS feeds and expert commentary | Identify and onboard initial fashion-technology RSS sources and expert commentary for the Technology vertical launch.
TECH-06 | Technology Vertical | Marketing | P1 | Mini-Apps Wave 1 | Position Technology vertical to fashion-tech founders | Craft outbound positioning and comms targeting fashion-tech founders and tool builders to drive early Technology vertical adoption. | Depends on TECH-01
LIFE-01 | Lifestyle Vertical | Engineering | P0 | Fashion/Tech/Lifestyle Taxonomy | Implement Lifestyle vertical landing route | Build the Lifestyle vertical landing route with subcategory tabs (Wellness/Interiors/Travel/Culture/Modern Living). | Depends on DISC-04
LIFE-02 | Lifestyle Vertical | Engineering | P1 | Fashion/Tech/Lifestyle Taxonomy | Add Lifestyle RSS sources and dedup rules | Add Lifestyle-specific RSS sources to the ingestion service, including any dedup rule adjustments needed for the new content type.
LIFE-03 | Lifestyle Vertical | Design | P0 | Fashion/Tech/Lifestyle Taxonomy | Design Lifestyle vertical homepage | Design the Lifestyle vertical homepage with rails for wellness, interiors, travel, and culture content.
LIFE-04 | Lifestyle Vertical | Design | P1 | Mini-Apps Wave 1 | Design cross-vertical navigation | Design navigation allowing users to follow and browse Fashion, Technology, and Lifestyle content together rather than in silos.
LIFE-05 | Lifestyle Vertical | Marketing | P0 | Fashion/Tech/Lifestyle Taxonomy | Validate Lifestyle vertical demand | Run a survey or waitlist with the target audience to validate demand for a Lifestyle vertical before heavy content investment.
LIFE-06 | Lifestyle Vertical | Marketing | P1 | Mini-Apps Wave 1 | Recruit Lifestyle creators and circles | Recruit an initial cohort of Lifestyle creators and seed Lifestyle-focused circles. | Depends on LIFE-05
TOOLS-01 | Tools Directory | Engineering | P1 | Mini-Apps Wave 1 | Build Tool Profile data model | Create the Tool Profile model covering name, company, overview, use cases, features, pricing, and integrations.
TOOLS-02 | Tools Directory | Engineering | P1 | Mini-Apps Wave 1 | Build Tools Directory browse and filter API | Build an API to browse and filter tools by use-case category (ideation, design, 3D, PLM, forecasting, etc.). | Depends on TOOLS-01
TOOLS-03 | Tools Directory | Engineering | P2 | Mini-Apps Wave 2 | Add save/compare tool actions | Add save and compare actions for tools, reusing the existing bookmarks/folders infrastructure where possible. | Depends on TOOLS-01
TOOLS-04 | Tools Directory | Design | P1 | Mini-Apps Wave 1 | Design Tools Directory browse grid and profile page | Design the browse grid and the detailed Tool Profile page. | Depends on TOOLS-01
TOOLS-05 | Tools Directory | Design | P2 | Mini-Apps Wave 2 | Design tool comparison view | Design a side-by-side comparison view for features and pricing across selected tools. | Depends on TOOLS-03
TOOLS-06 | Tools Directory | Marketing | P1 | Mini-Apps Wave 1 | Recruit initial tool vendors for directory launch | Recruit 20-30 fashion-tech tool vendors to populate the directory ahead of launch.
TOOLS-07 | Tools Directory | Marketing | P2 | Mini-Apps Wave 2 | Define sponsored-listing disclosure policy | Define and document a policy requiring mandatory disclosure labeling for any sponsored or partner tool listings.
EXPERT-01 | Expert Voices | Engineering | P1 | Mini-Apps Wave 1 | Add verified Expert Contributor role and profile fields | Add a verified Expert Contributor role with credential and affiliation profile fields, built on the existing role system.
EXPERT-02 | Expert Voices | Engineering | P1 | Mini-Apps Wave 1 | Build invite-and-verify workflow for Expert Voices | Build the invite-and-verify workflow for Expert Voices by extending the existing invite-gated role-upgrade system. | Depends on EXPERT-01
EXPERT-03 | Expert Voices | Engineering | P2 | Mini-Apps Wave 2 | Add Expert content type tagging | Add content-type tagging for expert contributions (thought leadership, opinion, analysis, case study). | Depends on EXPERT-01
EXPERT-04 | Expert Voices | Design | P1 | Mini-Apps Wave 1 | Design Expert Voices profile badge and Discover rail | Design a verified-expert profile badge and a dedicated Expert Voices content rail on Discover. | Depends on EXPERT-01
EXPERT-05 | Expert Voices | Design | P1 | Mini-Apps Wave 1 | Design expert application and verification flow | Design the screens for experts to apply and get verified. | Depends on EXPERT-02
EXPERT-06 | Expert Voices | Marketing | P0 | Mini-Apps Wave 1 | Recruit first cohort of named industry experts | Recruit 10-15 named fashion/tech industry experts as launch contributors for Expert Voices, prioritized ahead of other Wave-1 marketing work since it seeds Research and Q&A content later.
EXPERT-07 | Expert Voices | Marketing | P2 | Mini-Apps Wave 2 | Run Ask an Expert cross-promotion campaign | Run an Ask-an-Expert campaign to cross-promote Expert Voices with the Community Q&A mini-app. | Depends on EXPERT-01, QNA-01
RESEARCH-01 | Research & Intelligence | Engineering | P2 | Mini-Apps Wave 2 | Build Report content type with structured metadata | Build a Report/Research content type with metadata fields for report type, region, and downloadable asset.
RESEARCH-02 | Research & Intelligence | Engineering | P2 | Mini-Apps Wave 2 | Add gated download and lead-capture flow | Add a gated download flow with lead capture for research reports. | Depends on RESEARCH-01
RESEARCH-03 | Research & Intelligence | Design | P2 | Mini-Apps Wave 2 | Design Research hub and report detail template | Design the Research & Intelligence hub page and the report detail page template. | Depends on RESEARCH-01
RESEARCH-04 | Research & Intelligence | Design | P2 | Mini-Apps Wave 2 | Design report source-labeling treatment | Design a visual treatment for labeling report sources as Editorial, Research, or Partner content per governance principles.
RESEARCH-05 | Research & Intelligence | Marketing | P2 | Mini-Apps Wave 2 | Produce flagship trend report as anchor content | Produce a flagship 'State of Fashion Tech' trend report to anchor the Research & Intelligence mini-app launch. | Depends on RESEARCH-01
RESEARCH-06 | Research & Intelligence | Marketing | P2 | Mini-Apps Wave 2 | Build lead-gen funnel from report downloads | Build an email-capture funnel from report downloads into the broader marketing list. | Depends on RESEARCH-02
MEDIA-01 | Podcasts/Video/Live (Media) | Engineering | P2 | Mini-Apps Wave 2 | Add Media post type with embedded audio/video | Add a Media content type supporting embedded audio/video and a transcript field.
MEDIA-02 | Podcasts/Video/Live (Media) | Engineering | P2 | Mini-Apps Wave 2 | Add Media-specific feed filter | Add a podcast/video/interview filter to the existing shared filter system for Media content. | Depends on MEDIA-01
MEDIA-03 | Podcasts/Video/Live (Media) | Design | P2 | Mini-Apps Wave 2 | Design Media hub and player-embedded detail page | Design the Media hub grid and the detail page with embedded player. | Depends on MEDIA-01
MEDIA-04 | Podcasts/Video/Live (Media) | Marketing | P2 | Mini-Apps Wave 2 | Launch monthly interview series as flagship franchise | Launch a monthly 'Fashion Tech Voices' interview series to anchor the Media mini-app. | Depends on MEDIA-01
MEDIA-05 | Podcasts/Video/Live (Media) | Marketing | P2 | Mini-Apps Wave 2 | Distribute media content cross-platform | Distribute Media content on YouTube and Spotify with backlinks driving traffic back to Centoire. | Depends on MEDIA-04
MEDIA-06 | Podcasts/Video/Live (Media) | Engineering | P2 | Mini-Apps Wave 2 | Add basic view/play analytics for media content | Add basic play/view analytics tracking for Media content. | Depends on MEDIA-01
QNA-01 | Community Q&A & Showcase | Engineering | P2 | Mini-Apps Wave 2 | Build Q&A post type distinct from comments | Build a question/answer threaded content type separate from the existing comment system.
QNA-02 | Community Q&A & Showcase | Engineering | P2 | Mini-Apps Wave 2 | Add expert-answered flag to Q&A | Add an expert-answered flag tied to the verified Expert Voices role. | Depends on QNA-01, EXPERT-01
QNA-03 | Community Q&A & Showcase | Engineering | P2 | Mini-Apps Wave 2 | Build design-project Showcase post type | Build a Showcase content type for design projects and portfolios with gallery/media fields.
QNA-04 | Community Q&A & Showcase | Design | P2 | Mini-Apps Wave 2 | Design Q&A ask/answer flow | Design the ask/answer flow including the expert-answer highlight treatment. | Depends on QNA-01
QNA-05 | Community Q&A & Showcase | Design | P2 | Mini-Apps Wave 2 | Design Showcase gallery grid and submission flow | Design the Showcase gallery grid and the submission flow for creators. | Depends on QNA-03
QNA-06 | Community Q&A & Showcase | Marketing | P2 | Mini-Apps Wave 2 | Seed initial Showcase submissions via outreach | Seed the Showcase mini-app with initial submissions through design-school and creator outreach. | Depends on QNA-03
DIR-01 | Industry Directory | Engineering | P2 | Mini-Apps Wave 2 | Build Directory entity models | Build Directory entity models for People, Brands, Companies, and Institutions.
DIR-02 | Industry Directory | Engineering | P2 | Mini-Apps Wave 2 | Add claimable-profile flow | Add a flow allowing users/creators to claim a Directory entity as their own profile. | Depends on DIR-01
DIR-03 | Industry Directory | Design | P2 | Mini-Apps Wave 2 | Design Directory browse and entity profile templates | Design the Directory browse/search experience and the entity profile page template. | Depends on DIR-01
DIR-04 | Industry Directory | Design | P2 | Mini-Apps Wave 2 | Design claim-this-profile verification flow | Design the verification flow for a user claiming a Directory entity profile. | Depends on DIR-02
DIR-05 | Industry Directory | Marketing | P2 | Mini-Apps Wave 2 | Seed Directory with known fashion-tech entities | Pre-seed the Directory with 100+ known fashion-tech people, brands, and institutions before launch. | Depends on DIR-01
DIR-06 | Industry Directory | Marketing | P2 | Mini-Apps Wave 2 | Offer claimed-profile perks to drive claim rate | Offer verified badges and basic analytics as perks to encourage entities to claim their Directory profile. | Depends on DIR-02
LATER-01 | Learning | Engineering | P2 | Later | Park Learning/Education mini-app | Learning/Education (courses, tutorials, certifications) is parked pending stronger core engagement metrics and a larger base of expert-authored content to seed a curriculum. | Revisit after Expert Voices and Research & Intelligence traction
LATER-02 | Careers | Engineering | P2 | Later | Park Careers/Opportunities mini-app | Careers/Opportunities (jobs, internships, freelance) is parked pending sufficient claimed-profile density in Industry Directory and Expert Voices maturity. | Revisit after Directory claim-rate is meaningful
LATER-03 | Events | Engineering | P2 | Later | Park Events/Live Programming mini-app | Events and live programming are parked pending proven audience traction from the on-demand Media mini-app first. | Revisit after Media mini-app hits engagement targets
LATER-04 | Fashion Vertical | Marketing | P2 | Later | Park Beauty vertical expansion | Beauty as a fourth content vertical is explicitly out of scope for this plan; parked until Fashion, Technology, and Lifestyle show sustained traction. | Revisit per phased multi-vertical strategy
LATER-05 | Discover & Feed | Engineering | P2 | Later | Park Centoire Studio paid product | Centoire Studio (generative design, techpacks, brand kits, enterprise RBAC) is a separate future paid product, not sequenced in this community-focused plan. | Revisit after community monetization signal emerges

## Summary
Centoire Task Backlog — Summary
By Priority
Priority | Count
P0 | 19
P1 | 44
P2 | 47
By Track
Track | Count
Engineering | 55
Design | 30
Marketing | 25
By Mini-App x Priority
Mini-App | P0 | P1 | P2 | Total
Discover & Feed | 4 | 9 | 4 | 17
Community & Circles | 0 | 5 | 3 | 8
Moderation & Trust | 1 | 4 | 1 | 6
Notifications | 4 | 3 | 1 | 8
Reputation & Leaderboard | 0 | 4 | 2 | 6
Search | 0 | 2 | 3 | 5
Fashion Vertical | 3 | 3 | 1 | 7
Technology Vertical | 3 | 3 | 0 | 6
Lifestyle Vertical | 3 | 3 | 0 | 6
Tools Directory | 0 | 4 | 3 | 7
Expert Voices | 1 | 4 | 2 | 7
Research & Intelligence | 0 | 0 | 6 | 6
Podcasts/Video/Live (Media) | 0 | 0 | 6 | 6
Community Q&A & Showcase | 0 | 0 | 6 | 6
Industry Directory | 0 | 0 | 6 | 6
Learning | 0 | 0 | 1 | 1
Careers | 0 | 0 | 1 | 1
Events | 0 | 0 | 1 | 1